## SummaryPivot
Project Name | MA60365 - 2nd Source for Elasthane/Polyurethane

## SummaryData
SummaryID | Name | Type | ProjectNumber | ProjectName | FisYear | MID | FisMonth | FinYear_Month | value
1 | Summary Totals | Header | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 0
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 922.46
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 2 | JUN | 2020-JUN | 4000
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 3 | JUL | 2020-JUL | 0
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 4 | AUG | 2020-AUG | 7278.75
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 5 | SEP | 2020-SEP | 11700
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 6 | OCT | 2020-OCT | 1200
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 7 | NOV | 2020-NOV | 29200
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 8 | DEC | 2020-DEC | 29200
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 9 | JAN | 2020-JAN | 0
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 10 | FEB | 2020-FEB | 5000
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 11 | MAR | 2020-MAR | 5000
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 12 | APR | 2020-APR | 0
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 1 | MAY | 2021-MAY | 2399548.5
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 2 | JUN | 2021-JUN | 2159376.5
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 3 | JUL | 2021-JUL | 1704220
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 4 | AUG | 2021-AUG | 1726220
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 5 | SEP | 2021-SEP | 2166372.5
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 6 | OCT | 2021-OCT | 1698220
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 7 | NOV | 2021-NOV | 1698220
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 8 | DEC | 2021-DEC | 2126372.5
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 9 | JAN | 2021-JAN | 1698220
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 10 | FEB | 2021-FEB | 28850
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 11 | MAR | 2021-MAR | 21160
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 12 | APR | 2021-APR | 18850
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 1 | MAY | 2022-MAY | 630.5
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 2 | JUN | 2022-JUN | 0
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 3 | JUL | 2022-JUL | 4728.75
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 4 | AUG | 2022-AUG | 0
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 5 | SEP | 2022-SEP | 0
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 6 | OCT | 2022-OCT | 0
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 7 | NOV | 2022-NOV | 0
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 8 | DEC | 2022-DEC | 0
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 9 | JAN | 2022-JAN | 0
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 10 | FEB | 2022-FEB | 0
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 11 | MAR | 2022-MAR | 0
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 12 | APR | 2022-APR | 0
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 1 | MAY | 2023-MAY | 150217.11
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 2 | JUN | 2023-JUN | 22573.61
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 3 | JUL | 2023-JUL | 18058.89
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 4 | AUG | 2023-AUG | 18058.89
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 5 | SEP | 2023-SEP | 22573.61
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 6 | OCT | 2023-OCT | 29286.39
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 7 | NOV | 2023-NOV | 0
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 8 | DEC | 2023-DEC | 0
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 9 | JAN | 2023-JAN | 0
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 10 | FEB | 2023-FEB | 0
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 11 | MAR | 2023-MAR | 5130.37
2 | Total Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 12 | APR | 2023-APR | 4104.29
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 922.46
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 2 | JUN | 2020-JUN | 4000
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 3 | JUL | 2020-JUL | 0
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 4 | AUG | 2020-AUG | 7278.75
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 5 | SEP | 2020-SEP | 11700
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 6 | OCT | 2020-OCT | 1200
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 7 | NOV | 2020-NOV | 29200
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 8 | DEC | 2020-DEC | 29200
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 9 | JAN | 2020-JAN | 0
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 10 | FEB | 2020-FEB | 5000
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 11 | MAR | 2020-MAR | 5000
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 12 | APR | 2020-APR | 0
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 1 | MAY | 2021-MAY | 311886
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 2 | JUN | 2021-JUN | 71714
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 3 | JUL | 2021-JUL | 34090
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 4 | AUG | 2021-AUG | 56090
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 5 | SEP | 2021-SEP | 78710
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 6 | OCT | 2021-OCT | 28090
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 7 | NOV | 2021-NOV | 28090
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 8 | DEC | 2021-DEC | 38710
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 9 | JAN | 2021-JAN | 28090
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 10 | FEB | 2021-FEB | 28850
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 11 | MAR | 2021-MAR | 21160
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 12 | APR | 2021-APR | 18850
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 1 | MAY | 2022-MAY | 630.5
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 2 | JUN | 2022-JUN | 0
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 3 | JUL | 2022-JUL | 4728.75
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 4 | AUG | 2022-AUG | 0
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 5 | SEP | 2022-SEP | 0
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 6 | OCT | 2022-OCT | 0
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 7 | NOV | 2022-NOV | 0
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 8 | DEC | 2022-DEC | 0
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 9 | JAN | 2022-JAN | 0
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 10 | FEB | 2022-FEB | 0
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 11 | MAR | 2022-MAR | 0
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 12 | APR | 2022-APR | 0
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 1 | MAY | 2023-MAY | 150217.11
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 2 | JUN | 2023-JUN | 22573.61
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 3 | JUL | 2023-JUL | 18058.89
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 4 | AUG | 2023-AUG | 18058.89
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 5 | SEP | 2023-SEP | 22573.61
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 6 | OCT | 2023-OCT | 29286.39
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 7 | NOV | 2023-NOV | 0
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 8 | DEC | 2023-DEC | 0
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 9 | JAN | 2023-JAN | 0
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 10 | FEB | 2023-FEB | 0
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 11 | MAR | 2023-MAR | 5130.37
3 | Total Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 12 | APR | 2023-APR | 4104.29
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 1 | MAY | 2021-MAY | 2087662.5
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 2 | JUN | 2021-JUN | 2087662.5
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 3 | JUL | 2021-JUL | 1670130
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 4 | AUG | 2021-AUG | 1670130
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 5 | SEP | 2021-SEP | 2087662.5
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 6 | OCT | 2021-OCT | 1670130
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 7 | NOV | 2021-NOV | 1670130
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 8 | DEC | 2021-DEC | 2087662.5
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 9 | JAN | 2021-JAN | 1670130
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 10 | FEB | 2021-FEB | 0
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 11 | MAR | 2021-MAR | 0
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 12 | APR | 2021-APR | 0
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 1 | MAY | 2022-MAY | 0
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 2 | JUN | 2022-JUN | 0
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 3 | JUL | 2022-JUL | 0
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 4 | AUG | 2022-AUG | 0
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 5 | SEP | 2022-SEP | 0
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 6 | OCT | 2022-OCT | 0
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 7 | NOV | 2022-NOV | 0
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 8 | DEC | 2022-DEC | 0
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 9 | JAN | 2022-JAN | 0
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 10 | FEB | 2022-FEB | 0
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 11 | MAR | 2022-MAR | 0
4 | Total Non Site Project (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 12 | APR | 2022-APR | 0
5 | FTE $ Summary Totals | Header | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 0
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 922.46
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 2 | JUN | 2020-JUN | 4000
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 3 | JUL | 2020-JUL | 0
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 4 | AUG | 2020-AUG | 7278.75
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 5 | SEP | 2020-SEP | 11700
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 6 | OCT | 2020-OCT | 1200
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 7 | NOV | 2020-NOV | 29200
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 8 | DEC | 2020-DEC | 29200
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 9 | JAN | 2020-JAN | 0
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 10 | FEB | 2020-FEB | 5000
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 11 | MAR | 2020-MAR | 5000
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 12 | APR | 2020-APR | 0
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 1 | MAY | 2021-MAY | 311850
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 2 | JUN | 2021-JUN | 62100
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 3 | JUL | 2021-JUL | 24480
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 4 | AUG | 2021-AUG | 46480
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 5 | SEP | 2021-SEP | 69100
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 6 | OCT | 2021-OCT | 18480
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 7 | NOV | 2021-NOV | 18480
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 8 | DEC | 2021-DEC | 29100
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 9 | JAN | 2021-JAN | 18480
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 10 | FEB | 2021-FEB | 19240
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 11 | MAR | 2021-MAR | 11550
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 12 | APR | 2021-APR | 9240
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 1 | MAY | 2022-MAY | 630.5
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 2 | JUN | 2022-JUN | 0
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 3 | JUL | 2022-JUL | 4728.75
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 4 | AUG | 2022-AUG | 0
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 5 | SEP | 2022-SEP | 0
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 6 | OCT | 2022-OCT | 0
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 7 | NOV | 2022-NOV | 0
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 8 | DEC | 2022-DEC | 0
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 9 | JAN | 2022-JAN | 0
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 10 | FEB | 2022-FEB | 0
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 11 | MAR | 2022-MAR | 0
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 12 | APR | 2022-APR | 0
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 1 | MAY | 2023-MAY | 150217.11
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 2 | JUN | 2023-JUN | 22573.61
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 3 | JUL | 2023-JUL | 18058.89
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 4 | AUG | 2023-AUG | 18058.89
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 5 | SEP | 2023-SEP | 22573.61
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 6 | OCT | 2023-OCT | 29286.39
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 7 | NOV | 2023-NOV | 0
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 8 | DEC | 2023-DEC | 0
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 9 | JAN | 2023-JAN | 0
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 10 | FEB | 2023-FEB | 0
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 11 | MAR | 2023-MAR | 5130.37
6 | Total Project Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 12 | APR | 2023-APR | 4104.29
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 922.46
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 2 | JUN | 2020-JUN | 4000
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 3 | JUL | 2020-JUL | 0
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 4 | AUG | 2020-AUG | 7278.75
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 5 | SEP | 2020-SEP | 11700
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 6 | OCT | 2020-OCT | 1200
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 7 | NOV | 2020-NOV | 29200
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 8 | DEC | 2020-DEC | 29200
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 9 | JAN | 2020-JAN | 0
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 10 | FEB | 2020-FEB | 5000
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 11 | MAR | 2020-MAR | 5000
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 12 | APR | 2020-APR | 0
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 1 | MAY | 2021-MAY | 311850
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 2 | JUN | 2021-JUN | 62100
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 3 | JUL | 2021-JUL | 24480
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 4 | AUG | 2021-AUG | 46480
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 5 | SEP | 2021-SEP | 69100
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 6 | OCT | 2021-OCT | 18480
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 7 | NOV | 2021-NOV | 18480
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 8 | DEC | 2021-DEC | 29100
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 9 | JAN | 2021-JAN | 18480
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 10 | FEB | 2021-FEB | 19240
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 11 | MAR | 2021-MAR | 11550
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 12 | APR | 2021-APR | 9240
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 1 | MAY | 2022-MAY | 630.5
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 2 | JUN | 2022-JUN | 0
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 3 | JUL | 2022-JUL | 4728.75
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 4 | AUG | 2022-AUG | 0
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 5 | SEP | 2022-SEP | 0
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 6 | OCT | 2022-OCT | 0
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 7 | NOV | 2022-NOV | 0
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 8 | DEC | 2022-DEC | 0
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 9 | JAN | 2022-JAN | 0
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 10 | FEB | 2022-FEB | 0
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 11 | MAR | 2022-MAR | 0
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 12 | APR | 2022-APR | 0
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 1 | MAY | 2023-MAY | 150217.11
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 2 | JUN | 2023-JUN | 22573.61
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 3 | JUL | 2023-JUL | 18058.89
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 4 | AUG | 2023-AUG | 18058.89
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 5 | SEP | 2023-SEP | 22573.61
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 6 | OCT | 2023-OCT | 29286.39
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 7 | NOV | 2023-NOV | 0
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 8 | DEC | 2023-DEC | 0
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 9 | JAN | 2023-JAN | 0
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 10 | FEB | 2023-FEB | 0
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 11 | MAR | 2023-MAR | 5130.37
7 | Total Site Operating Expense | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 12 | APR | 2023-APR | 4104.29
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 0
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 2 | JUN | 2020-JUN | 0
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 3 | JUL | 2020-JUL | 0
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 4 | AUG | 2020-AUG | 0
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 5 | SEP | 2020-SEP | 0
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 6 | OCT | 2020-OCT | 0
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 7 | NOV | 2020-NOV | 0
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 8 | DEC | 2020-DEC | 0
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 9 | JAN | 2020-JAN | 0
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 10 | FEB | 2020-FEB | 0
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 11 | MAR | 2020-MAR | 0
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 12 | APR | 2020-APR | 0
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 1 | MAY | 2021-MAY | 311850
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 2 | JUN | 2021-JUN | 23100
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 3 | JUL | 2021-JUL | 18480
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 4 | AUG | 2021-AUG | 18480
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 5 | SEP | 2021-SEP | 23100
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 6 | OCT | 2021-OCT | 18480
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 7 | NOV | 2021-NOV | 18480
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 8 | DEC | 2021-DEC | 23100
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 9 | JAN | 2021-JAN | 18480
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 10 | FEB | 2021-FEB | 9240
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 11 | MAR | 2021-MAR | 11550
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 12 | APR | 2021-APR | 9240
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 1 | MAY | 2023-MAY | 150217.11
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 2 | JUN | 2023-JUN | 22573.61
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 3 | JUL | 2023-JUL | 18058.89
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 4 | AUG | 2023-AUG | 18058.89
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 5 | SEP | 2023-SEP | 22573.61
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 6 | OCT | 2023-OCT | 18058.89
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 7 | NOV | 2023-NOV | 0
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 8 | DEC | 2023-DEC | 0
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 9 | JAN | 2023-JAN | 0
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 10 | FEB | 2023-FEB | 0
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 11 | MAR | 2023-MAR | 5130.37
8 | Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 12 | APR | 2023-APR | 4104.29
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 922.46
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 2 | JUN | 2020-JUN | 4000
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 3 | JUL | 2020-JUL | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 4 | AUG | 2020-AUG | 7278.75
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 5 | SEP | 2020-SEP | 11700
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 6 | OCT | 2020-OCT | 1200
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 7 | NOV | 2020-NOV | 29200
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 8 | DEC | 2020-DEC | 29200
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 9 | JAN | 2020-JAN | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 10 | FEB | 2020-FEB | 5000
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 11 | MAR | 2020-MAR | 5000
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 12 | APR | 2020-APR | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 2 | JUN | 2021-JUN | 39000
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 3 | JUL | 2021-JUL | 6000
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 4 | AUG | 2021-AUG | 28000
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 5 | SEP | 2021-SEP | 46000
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 8 | DEC | 2021-DEC | 6000
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 10 | FEB | 2021-FEB | 10000
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 1 | MAY | 2022-MAY | 630.5
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 2 | JUN | 2022-JUN | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 3 | JUL | 2022-JUL | 4728.75
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 4 | AUG | 2022-AUG | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 5 | SEP | 2022-SEP | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 6 | OCT | 2022-OCT | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 7 | NOV | 2022-NOV | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 8 | DEC | 2022-DEC | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 9 | JAN | 2022-JAN | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 10 | FEB | 2022-FEB | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 11 | MAR | 2022-MAR | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 12 | APR | 2022-APR | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 1 | MAY | 2023-MAY | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 2 | JUN | 2023-JUN | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 3 | JUL | 2023-JUL | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 4 | AUG | 2023-AUG | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 5 | SEP | 2023-SEP | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 6 | OCT | 2023-OCT | 11227.5
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 7 | NOV | 2023-NOV | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 8 | DEC | 2023-DEC | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 9 | JAN | 2023-JAN | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 10 | FEB | 2023-FEB | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 11 | MAR | 2023-MAR | 0
9 | Site Operating DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 12 | APR | 2023-APR | 0
10 | Site Non Project Charging Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 0
11 | Total Non Site Operating Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 0
12 | FTE Capital Totals | Header | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 0
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 1 | MAY | 2021-MAY | 2087698.5
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 2 | JUN | 2021-JUN | 2097276.5
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 3 | JUL | 2021-JUL | 1679740
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 4 | AUG | 2021-AUG | 1679740
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 5 | SEP | 2021-SEP | 2097272.5
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 6 | OCT | 2021-OCT | 1679740
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 7 | NOV | 2021-NOV | 1679740
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 8 | DEC | 2021-DEC | 2097272.5
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 9 | JAN | 2021-JAN | 1679740
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 10 | FEB | 2021-FEB | 9610
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 11 | MAR | 2021-MAR | 9610
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 12 | APR | 2021-APR | 9610
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 1 | MAY | 2022-MAY | 0
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 2 | JUN | 2022-JUN | 0
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 3 | JUL | 2022-JUL | 0
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 4 | AUG | 2022-AUG | 0
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 5 | SEP | 2022-SEP | 0
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 6 | OCT | 2022-OCT | 0
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 7 | NOV | 2022-NOV | 0
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 8 | DEC | 2022-DEC | 0
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 9 | JAN | 2022-JAN | 0
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 10 | FEB | 2022-FEB | 0
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 11 | MAR | 2022-MAR | 0
13 | Total Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 12 | APR | 2022-APR | 0
14 | Total Site Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 1 | MAY | 2021-MAY | 36
14 | Total Site Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 2 | JUN | 2021-JUN | 9614
14 | Total Site Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 3 | JUL | 2021-JUL | 9610
14 | Total Site Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 4 | AUG | 2021-AUG | 9610
14 | Total Site Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 5 | SEP | 2021-SEP | 9610
14 | Total Site Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 6 | OCT | 2021-OCT | 9610
14 | Total Site Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 7 | NOV | 2021-NOV | 9610
14 | Total Site Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 8 | DEC | 2021-DEC | 9610
14 | Total Site Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 9 | JAN | 2021-JAN | 9610
14 | Total Site Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 10 | FEB | 2021-FEB | 9610
14 | Total Site Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 11 | MAR | 2021-MAR | 9610
14 | Total Site Capital | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 12 | APR | 2021-APR | 9610
15 | Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 0
16 | Site Capital DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 1 | MAY | 2021-MAY | 36
16 | Site Capital DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 2 | JUN | 2021-JUN | 9614
16 | Site Capital DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 3 | JUL | 2021-JUL | 9610
16 | Site Capital DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 4 | AUG | 2021-AUG | 9610
16 | Site Capital DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 5 | SEP | 2021-SEP | 9610
16 | Site Capital DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 6 | OCT | 2021-OCT | 9610
16 | Site Capital DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 7 | NOV | 2021-NOV | 9610
16 | Site Capital DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 8 | DEC | 2021-DEC | 9610
16 | Site Capital DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 9 | JAN | 2021-JAN | 9610
16 | Site Capital DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 10 | FEB | 2021-FEB | 9610
16 | Site Capital DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 11 | MAR | 2021-MAR | 9610
16 | Site Capital DE | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 12 | APR | 2021-APR | 9610
17 | Site Non Project Charging Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 0
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 1 | MAY | 2021-MAY | 2087662.5
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 2 | JUN | 2021-JUN | 2087662.5
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 3 | JUL | 2021-JUL | 1670130
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 4 | AUG | 2021-AUG | 1670130
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 5 | SEP | 2021-SEP | 2087662.5
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 6 | OCT | 2021-OCT | 1670130
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 7 | NOV | 2021-NOV | 1670130
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 8 | DEC | 2021-DEC | 2087662.5
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 9 | JAN | 2021-JAN | 1670130
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 10 | FEB | 2021-FEB | 0
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 11 | MAR | 2021-MAR | 0
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 12 | APR | 2021-APR | 0
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 1 | MAY | 2022-MAY | 0
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 2 | JUN | 2022-JUN | 0
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 3 | JUL | 2022-JUL | 0
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 4 | AUG | 2022-AUG | 0
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 5 | SEP | 2022-SEP | 0
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 6 | OCT | 2022-OCT | 0
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 7 | NOV | 2022-NOV | 0
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 8 | DEC | 2022-DEC | 0
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 9 | JAN | 2022-JAN | 0
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 10 | FEB | 2022-FEB | 0
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 11 | MAR | 2022-MAR | 0
18 | Total Non Site Capital Labor | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 12 | APR | 2022-APR | 0
19 | FTE Summary Totals | Header | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 0
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 30.33
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 2 | JUN | 2020-JUN | 7.98
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 3 | JUL | 2020-JUL | 7.98
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 4 | AUG | 2020-AUG | 9.93
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 5 | SEP | 2020-SEP | 9.93
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 6 | OCT | 2020-OCT | 9.93
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 7 | NOV | 2020-NOV | 10.03
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 8 | DEC | 2020-DEC | 10.03
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 9 | JAN | 2020-JAN | 10.03
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 10 | FEB | 2020-FEB | 9.73
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 11 | MAR | 2020-MAR | 9.73
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 12 | APR | 2020-APR | 10.96
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 1 | MAY | 2021-MAY | 129.29
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 2 | JUN | 2021-JUN | 114.05
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 3 | JUL | 2021-JUL | 114.05
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 4 | AUG | 2021-AUG | 114.05
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 5 | SEP | 2021-SEP | 114.05
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 6 | OCT | 2021-OCT | 114.05
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 7 | NOV | 2021-NOV | 114.05
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 8 | DEC | 2021-DEC | 114.05
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 9 | JAN | 2021-JAN | 114.05
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 10 | FEB | 2021-FEB | 5
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 11 | MAR | 2021-MAR | 5
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 12 | APR | 2021-APR | 5
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 1 | MAY | 2022-MAY | 0
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 2 | JUN | 2022-JUN | 0
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 3 | JUL | 2022-JUL | 0
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 4 | AUG | 2022-AUG | 0
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 5 | SEP | 2022-SEP | 0
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 6 | OCT | 2022-OCT | 0
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 7 | NOV | 2022-NOV | 0
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 8 | DEC | 2022-DEC | 0
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 9 | JAN | 2022-JAN | 0
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 10 | FEB | 2022-FEB | 0
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 11 | MAR | 2022-MAR | 0
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 12 | APR | 2022-APR | 0
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 1 | MAY | 2023-MAY | 9.15
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 2 | JUN | 2023-JUN | 1.1
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 3 | JUL | 2023-JUL | 1.1
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 4 | AUG | 2023-AUG | 1.1
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 5 | SEP | 2023-SEP | 1.1
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 6 | OCT | 2023-OCT | 1.1
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 7 | NOV | 2023-NOV | 0
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 8 | DEC | 2023-DEC | 0
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 9 | JAN | 2023-JAN | 0
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 10 | FEB | 2023-FEB | 0
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 11 | MAR | 2023-MAR | 0.25
20 | Total Project FTEs (Operating & Capital) | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 12 | APR | 2023-APR | 0.25
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 30.33
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 2 | JUN | 2020-JUN | 7.98
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 3 | JUL | 2020-JUL | 7.98
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 4 | AUG | 2020-AUG | 9.93
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 5 | SEP | 2020-SEP | 9.93
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 6 | OCT | 2020-OCT | 9.93
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 7 | NOV | 2020-NOV | 10.03
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 8 | DEC | 2020-DEC | 10.03
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 9 | JAN | 2020-JAN | 10.03
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 10 | FEB | 2020-FEB | 9.73
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 11 | MAR | 2020-MAR | 9.73
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 12 | APR | 2020-APR | 10.96
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 1 | MAY | 2021-MAY | 16.2
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 2 | JUN | 2021-JUN | 1.2
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 3 | JUL | 2021-JUL | 1.2
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 4 | AUG | 2021-AUG | 1.2
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 5 | SEP | 2021-SEP | 1.2
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 6 | OCT | 2021-OCT | 1.2
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 7 | NOV | 2021-NOV | 1.2
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 8 | DEC | 2021-DEC | 1.2
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 9 | JAN | 2021-JAN | 1.2
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 10 | FEB | 2021-FEB | 0.6
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 11 | MAR | 2021-MAR | 0.6
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 12 | APR | 2021-APR | 0.6
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 1 | MAY | 2023-MAY | 9.15
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 2 | JUN | 2023-JUN | 1.1
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 3 | JUL | 2023-JUL | 1.1
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 4 | AUG | 2023-AUG | 1.1
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 5 | SEP | 2023-SEP | 1.1
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 6 | OCT | 2023-OCT | 1.1
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 7 | NOV | 2023-NOV | 0
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 8 | DEC | 2023-DEC | 0
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 9 | JAN | 2023-JAN | 0
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 10 | FEB | 2023-FEB | 0
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 11 | MAR | 2023-MAR | 0.25
21 | Total Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 12 | APR | 2023-APR | 0.25
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 30.33
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 2 | JUN | 2020-JUN | 7.98
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 3 | JUL | 2020-JUL | 7.98
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 4 | AUG | 2020-AUG | 9.93
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 5 | SEP | 2020-SEP | 9.93
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 6 | OCT | 2020-OCT | 9.93
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 7 | NOV | 2020-NOV | 10.03
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 8 | DEC | 2020-DEC | 10.03
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 9 | JAN | 2020-JAN | 10.03
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 10 | FEB | 2020-FEB | 9.73
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 11 | MAR | 2020-MAR | 9.73
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 12 | APR | 2020-APR | 10.96
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 1 | MAY | 2021-MAY | 16.2
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 2 | JUN | 2021-JUN | 1.2
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 3 | JUL | 2021-JUL | 1.2
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 4 | AUG | 2021-AUG | 1.2
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 5 | SEP | 2021-SEP | 1.2
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 6 | OCT | 2021-OCT | 1.2
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 7 | NOV | 2021-NOV | 1.2
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 8 | DEC | 2021-DEC | 1.2
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 9 | JAN | 2021-JAN | 1.2
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 10 | FEB | 2021-FEB | 0.6
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 11 | MAR | 2021-MAR | 0.6
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 12 | APR | 2021-APR | 0.6
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 1 | MAY | 2023-MAY | 9.15
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 2 | JUN | 2023-JUN | 1.1
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 3 | JUL | 2023-JUL | 1.1
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 4 | AUG | 2023-AUG | 1.1
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 5 | SEP | 2023-SEP | 1.1
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 6 | OCT | 2023-OCT | 1.1
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 7 | NOV | 2023-NOV | 0
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 8 | DEC | 2023-DEC | 0
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 9 | JAN | 2023-JAN | 0
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 10 | FEB | 2023-FEB | 0
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 11 | MAR | 2023-MAR | 0.25
22 | Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2023 | 12 | APR | 2023-APR | 0.25
23 | Site Non Project Charging FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 0
24 | Total Non Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 0
25 | Non Site Operating FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 0
26 | Non Site Non Project Charging FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 0
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 1 | MAY | 2021-MAY | 113.09
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 2 | JUN | 2021-JUN | 112.85
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 3 | JUL | 2021-JUL | 112.85
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 4 | AUG | 2021-AUG | 112.85
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 5 | SEP | 2021-SEP | 112.85
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 6 | OCT | 2021-OCT | 112.85
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 7 | NOV | 2021-NOV | 112.85
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 8 | DEC | 2021-DEC | 112.85
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 9 | JAN | 2021-JAN | 112.85
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 10 | FEB | 2021-FEB | 4.4
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 11 | MAR | 2021-MAR | 4.4
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 12 | APR | 2021-APR | 4.4
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 1 | MAY | 2022-MAY | 0
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 2 | JUN | 2022-JUN | 0
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 3 | JUL | 2022-JUL | 0
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 4 | AUG | 2022-AUG | 0
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 5 | SEP | 2022-SEP | 0
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 6 | OCT | 2022-OCT | 0
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 7 | NOV | 2022-NOV | 0
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 8 | DEC | 2022-DEC | 0
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 9 | JAN | 2022-JAN | 0
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 10 | FEB | 2022-FEB | 0
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 11 | MAR | 2022-MAR | 0
27 | Total Site and Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 12 | APR | 2022-APR | 0
28 | Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 0
29 | Site Non Project Charge Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2020 | 1 | MAY | 2020-MAY | 0
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 1 | MAY | 2021-MAY | 108.45
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 2 | JUN | 2021-JUN | 108.45
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 3 | JUL | 2021-JUL | 108.45
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 4 | AUG | 2021-AUG | 108.45
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 5 | SEP | 2021-SEP | 108.45
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 6 | OCT | 2021-OCT | 108.45
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 7 | NOV | 2021-NOV | 108.45
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 8 | DEC | 2021-DEC | 108.45
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 9 | JAN | 2021-JAN | 108.45
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 10 | FEB | 2021-FEB | 0
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 11 | MAR | 2021-MAR | 0
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 12 | APR | 2021-APR | 0
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 1 | MAY | 2022-MAY | 0
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 2 | JUN | 2022-JUN | 0
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 3 | JUL | 2022-JUL | 0
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 4 | AUG | 2022-AUG | 0
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 5 | SEP | 2022-SEP | 0
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 6 | OCT | 2022-OCT | 0
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 7 | NOV | 2022-NOV | 0
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 8 | DEC | 2022-DEC | 0
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 9 | JAN | 2022-JAN | 0
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 10 | FEB | 2022-FEB | 0
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 11 | MAR | 2022-MAR | 0
30 | Non Site Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2022 | 12 | APR | 2022-APR | 0
31 | Non Site Non Project Charge Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 1 | MAY | 2021-MAY | 4.64
31 | Non Site Non Project Charge Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 2 | JUN | 2021-JUN | 4.4
31 | Non Site Non Project Charge Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 3 | JUL | 2021-JUL | 4.4
31 | Non Site Non Project Charge Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 4 | AUG | 2021-AUG | 4.4
31 | Non Site Non Project Charge Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 5 | SEP | 2021-SEP | 4.4
31 | Non Site Non Project Charge Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 6 | OCT | 2021-OCT | 4.4
31 | Non Site Non Project Charge Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 7 | NOV | 2021-NOV | 4.4
31 | Non Site Non Project Charge Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 8 | DEC | 2021-DEC | 4.4
31 | Non Site Non Project Charge Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 9 | JAN | 2021-JAN | 4.4
31 | Non Site Non Project Charge Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 10 | FEB | 2021-FEB | 4.4
31 | Non Site Non Project Charge Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 11 | MAR | 2021-MAR | 4.4
31 | Non Site Non Project Charge Capital FTEs | Child | MA60365 | 2nd Source for Elasthane/Polyurethane | 2021 | 12 | APR | 2021-APR | 4.4

## Resource
Project Name | MA60365 - 2nd Source for Elasthane/Polyurethane
WBSNumber | Business | BusinessUnit | HighOrg | MidOrg | Team | RequiredSkill | FinYear | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | Comments
MA60365.MEC | NA | CRHF | MECC (PRO) Total Roll-up | Process and Component Development - R&D | Polymer Dev | Development Eng | 2020 | 6.05 | 0.5 | 0.6 | 1.15 | 1.15 | 1.15 | 1.2 | 1.2 | 1.2 | 1.1 | 1.1 | 1.1 | Molding
MA60365.MEC | NA | CRHF | MECC (PRO) Total Roll-up | Process and Component Development - R&D | Polymer Dev | Laser Weld Eng | 2020 | MAY: 0.05; JUN: 0.05; JUL: 0.05; AUG: 0.05; SEP: 0.05; OCT: 0.05; APR: 1.23 | If tool revisions needed
MA60365.MEC | NA | CRHF | MECC (PRO) Total Roll-up | Process and Component Development - R&D | Polymer Dev | Dev Tech | 2023 | MAY: 2.05; JUN: 0.3; JUL: 0.3; AUG: 0.3; SEP: 0.3; OCT: 0.3 | Molding
MA60365.MEC | NA | CRHF | MECC (PRO) Total Roll-up | Process and Component Development - R&D | Polymer Dev | Dev Tech | 2020 | 6.03 | 6.03 | 6.03 | 6.03 | 6.03 | 6.03 | 6.03 | 6.03 | 6.03 | 6.03 | 6.03 | 6.03 | Molding
MA60365.MEC | NA | CRHF | MECC (PRO) Total Roll-up | Process and Component Development - R&D | Polymer Dev | Dev Tech | 2020 | 6.05 | 0.5 | 0.6 | 1.15 | 1.15 | 1.15 | 1.2 | 1.2 | 1.2 | 1.1 | 1.1 | 1.1 | Molding
MA60365.MEC | NA | CRHF | MECC (PRO) Total Roll-up | Process and Component Development - R&D | Polymer Dev | Dev Tech | 2020 | 3.05 | 0.15 | 0.05 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | Molding
MA60365.MEC | NA | CRHF | MECC (PRO) Total Roll-up | MECC Quality - Quality Engineers | MECC Destructive Analysis | Scientist | 2021 | 4.05 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.15 | 0.15 | 0.15 | Molding
MA60365.MEC | NA | CRHF | MECC (PRO) Total Roll-up | Process and Component Development - R&D | Polymer Dev | Dev Tech | 2023 | 5.05 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  |  | 0.25 | 0.25 | Molding
MA60365.MEC | NA | CRHF | MECC (PRO) Total Roll-up | MECC Quality - Quality Engineers | MECC Destructive Analysis | Scientist | 2021 | 4.05 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.15 | 0.15 | 0.15 | Molding
MA60365.MEC | NA | CRHF | MECC (PRO) Total Roll-up | MECC Quality - Quality Engineers | MECC Destructive Analysis | Project Coordinator | 2020 | 6.05 | 0.6 | 0.6 | 1.15 | 1.15 | 1.15 | 1.2 | 1.2 | 1.2 | 1.1 | 1.1 | 1.1 | Molding
MA60365.MEC | NA | CRHF | MECC (PRO) Total Roll-up | Process and Component Development - R&D | Polymer Dev | Dev Tech | 2021 | 4.05 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.15 | 0.15 | 0.15 | Molding
MA60365.MEC | NA | CRHF | MECC (PRO) Total Roll-up | MECC Quality - Quality Engineers | MECC Destructive Analysis | Scientist | 2021 | 4.05 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.15 | 0.15 | 0.15 | Molding
MA60365.MEC | NA | CRHF | MECC (PRO) Total Roll-up | Process and Component Development - R&D | Polymer Dev | Dev Tech | 2023 | MAY: 2.05; JUN: 0.3; JUL: 0.3; AUG: 0.3; SEP: 0.3; OCT: 0.3 | Molding
MA60365.MEC | NA | CRHF | MECC (PRO) Total Roll-up | Process and Component Development - R&D | Polymer Dev | Dev Tech | 2020 | 3.05 | 0.15 | 0.05 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | Molding

## Capital
Project Name | MA60365 - 2nd Source for Elasthane/Polyurethane
WBSNumber | Priority | Impactofnotinvesting | CapitalCategory | CapitalType | Description | AOPProject | FinYear | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR
TBD | High | Test Impact | Cost Reduction | Capital Interest | Test desc | Analytical QC Instrament Replacements | 2021 | 8 | 1204 | 1204 | 1204 | 1204 | 1204 | 1204 | 1204 | 1204 | 1204 | 1204 | 1204
TBD | Medium | Test Impact | Cost Reduction | Capital Interest | Test desc | COS Transformation - Press 1, 17, and 29 | 2021 | 1 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200
TBD | Medium | Test Impact | Cost Reduction | Capital Interest | Test desc | COS Transformation - Press 1, 17, and 29 | 2021 | 2 | 1202 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200
TBD | Medium | Test Impact | Cost Reduction | Capital Interest | Test desc | COS Transformation - Press 1, 17, and 29 | 2021 | 3 | 1202 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200
TBD | High | Test Impact | Cost Reduction | Capital Interest | Test desc | Analytical QC Instrament Replacements | 2021 | 7 | 1203 | 1203 | 1203 | 1203 | 1203 | 1203 | 1203 | 1203 | 1203 | 1203 | 1203
TBD | Medium | Test Impact | Cost Reduction | Capital Interest | Test desc | COS Transformation - Press 1, 17, and 29 | 2021 | 4 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200
TBD | Medium | Test Impact | Cost Reduction | Capital Interest | Test desc | COS Transformation - Press 1, 17, and 29 | 2021 | 5 | 1201 | 1201 | 1201 | 1201 | 1201 | 1201 | 1201 | 1201 | 1201 | 1201 | 1201
TBD | Medium | Test Impact | Cost Reduction | Capital Interest | Test desc | Analytical QC Instrament Replacements | 2021 | 6 | 1202 | 1202 | 1202 | 1202 | 1202 | 1202 | 1202 | 1202 | 1202 | 1202 | 1202
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-Very High 2-High 3-Medium 4-Low 5-Very Low

## CapitalLabor
Project Name | MA60365 - 2nd Source for Elasthane/Polyurethane
WBSNumber | Business | BusinessUnit | HighOrg | MidOrg | Team | RequiredSkill | Priority | CapitalCategory | AOPProject | FinYear | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR
TBD | NA | CRHF | CVG Global Supply Management | Technical Sourcing | Technical Sourcing | Management | High | BCP | Arbin Replacement | 2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TBD | NA | CRHF | CVG Global Supply Management | Component Engineering | AFS (Rheault) | Component Eng | High | BCP | Analytical QC Instrament Replacements | 2021 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0 | 0 | 0
TBD | NA | CRHF | CVG Global Supply Management | Component Engineering | AFS (Rheault) | Component Eng | High | BCP | Analytical QC Instrament Replacements | 2021 | 1.23 | 1.23 | 1.23 | 1.23 | 1.23 | 1.23 | 1.23 | 1.23 | 1.23 | 0 | 0 | 0
TBD | NA | Other | Other | Non-MECC - Burden Non-charging (FTE) | Moundsview Burden (Non charging) | NA | High | BCP | Analytical QC Instrament Replacements | 2021 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33
TBD | NA | Other | Other | Non-MECC - Burden Non-charging (FTE) | Moundsview Burden (Non charging) | NA | High | BCP | Analytical QC Instrament Replacements | 2021 | 0.25 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22
TBD | NA | Other | Other | Non-MECC - Burden Non-charging (FTE) | Moundsview Burden (Non charging) | NA | High | BCP | Analytical QC Instrament Replacements | 2021 | 0.25 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22
TBD | NA | Other | Other | Non-MECC - Burden Non-charging (FTE) | Moundsview Burden (Non charging) | NA | High | BCP | Analytical QC Instrament Replacements | 2021 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33
TBD | NA | CRHF | CVG Global Supply Management | Component Engineering | AFS (Rheault) | Component Eng | High | BCP | Analytical QC Instrament Replacements | 2021 | 2.23 | 2.23 | 2.23 | 2.23 | 2.23 | 2.23 | 2.23 | 2.23 | 2.23 | 0 | 0 | 0
TBD | NA | CRHF | CVG Global Supply Management | Component Engineering | AFS (Rheault) | Component Eng | High | BCP | Analytical QC Instrament Replacements | 2021 | 3.23 | 3.23 | 3.23 | 3.23 | 3.23 | 3.23 | 3.23 | 3.23 | 3.23 | 0 | 0 | 0
TBD | NA | CRHF | CVG Global Supply Management | Component Engineering | AFS (Rheault) | Component Eng | High | BCP | Analytical QC Instrament Replacements | 2021 | 4.23 | 4.23 | 4.23 | 4.23 | 4.23 | 4.23 | 4.23 | 4.23 | 4.23 | 0 | 0 | 0
TBD | NA | CRHF | CVG Global Supply Management | Component Engineering | AFS (Rheault) | Component Eng | High | BCP | Analytical QC Instrament Replacements | 2021 | 5.23 | 5.23 | 5.23 | 5.23 | 5.23 | 5.23 | 5.23 | 5.23 | 5.23 | 0 | 0 | 0
TBD | NA | Other | Other | Non-MECC - Burden Non-charging (FTE) | Moundsview Burden (Non charging) | NA | High | BCP | Analytical QC Instrament Replacements | 2021 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33
TBD | NA | Other | Other | Non-MECC - Burden Non-charging (FTE) | Moundsview Burden (Non charging) | NA | High | BCP | Analytical QC Instrament Replacements | 2021 | 0.25 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22
TBD | NA | Other | Other | Non-MECC - Burden Non-charging (FTE) | Moundsview Burden (Non charging) | NA | High | BCP | Analytical QC Instrament Replacements | 2021 | 0.25 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22
TBD | NA | Other | Other | Non-MECC - Burden Non-charging (FTE) | Moundsview Burden (Non charging) | NA | High | BCP | Analytical QC Instrament Replacements | 2021 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33
TBD | NA | CRHF | CVG Global Supply Management | Component Engineering | AFS (Rheault) | Component Eng | High | BCP | Analytical QC Instrament Replacements | 2021 | 6.23 | 6.23 | 6.23 | 6.23 | 6.23 | 6.23 | 6.23 | 6.23 | 6.23 | 0 | 0 | 0
TBD | NA | CRHF | CVG Global Supply Management | Component Engineering | AFS (Rheault) | Component Eng | High | BCP | Analytical QC Instrament Replacements | 2021 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 0 | 0 | 0
TBD | NA | CRHF | CVG Global Supply Management | Component Engineering | AFS (Rheault) | Component Eng | High | BCP | Analytical QC Instrament Replacements | 2021 | 8.23 | 8.23 | 8.23 | 8.23 | 8.23 | 8.23 | 8.23 | 8.23 | 8.23 | 0 | 0 | 0
TBD | NA | CRHF | CVG Global Supply Management | Component Engineering | AFS (Rheault) | Component Eng | High | BCP | Analytical QC Instrament Replacements | 2021 | 9.23 | 9.23 | 9.23 | 9.23 | 9.23 | 9.23 | 9.23 | 9.23 | 9.23 | 0 | 0 | 0
TBD | NA | Other | Other | Non-MECC - Burden Non-charging (FTE) | Moundsview Burden (Non charging) | NA | High | BCP | Analytical QC Instrament Replacements | 2021 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33
TBD | NA | Other | Other | Non-MECC - Burden Non-charging (FTE) | Moundsview Burden (Non charging) | NA | High | BCP | Analytical QC Instrament Replacements | 2021 | 0.25 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22
TBD | NA | Other | Other | Non-MECC - Burden Non-charging (FTE) | Moundsview Burden (Non charging) | NA | High | BCP | Analytical QC Instrament Replacements | 2021 | 0.25 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22
TBD | NA | Other | Other | Non-MECC - Burden Non-charging (FTE) | Moundsview Burden (Non charging) | NA | High | BCP | Analytical QC Instrament Replacements | 2021 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33
TBD | NA | CRHF | CVG Global Supply Management | Component Engineering | AFS (Rheault) | Component Eng | High | BCP | Analytical QC Instrament Replacements | 2021 | 10.23 | 10.23 | 10.23 | 10.23 | 10.23 | 10.23 | 10.23 | 10.23 | 10.23 | 0 | 0 | 0
TBD | NA | CRHF | CVG Global Supply Management | Component Engineering | AFS (Rheault) | Component Eng | High | BCP | Analytical QC Instrament Replacements | 2021 | 11.23 | 11.23 | 11.23 | 11.23 | 11.23 | 11.23 | 11.23 | 11.23 | 11.23 | 0 | 0 | 0
TBD | NA | CRHF | CVG Global Supply Management | Component Engineering | AFS (Rheault) | Component Eng | High | BCP | Analytical QC Instrament Replacements | 2021 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 0 | 0 | 0
TBD | NA | CRHF | CVG Global Supply Management | Component Engineering | AFS (Rheault) | Component Eng | High | BCP | Analytical QC Instrament Replacements | 2021 | 13.23 | 13.23 | 13.23 | 13.23 | 13.23 | 13.23 | 13.23 | 13.23 | 13.23 | 0 | 0 | 0
TBD | NA | Other | Other | Non-MECC - Burden Non-charging (FTE) | Moundsview Burden (Non charging) | NA | High | BCP | Analytical QC Instrament Replacements | 2021 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33
TBD | NA | Other | Other | Non-MECC - Burden Non-charging (FTE) | Moundsview Burden (Non charging) | NA | High | BCP | Analytical QC Instrament Replacements | 2021 | 0.25 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22
TBD | NA | Other | Other | Non-MECC - Burden Non-charging (FTE) | Moundsview Burden (Non charging) | NA | High | BCP | Analytical QC Instrament Replacements | 2021 | 0.25 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22
TBD | NA | Other | Other | Non-MECC - Burden Non-charging (FTE) | Moundsview Burden (Non charging) | NA | High | BCP | Analytical QC Instrament Replacements | 2021 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33
TBD | NA | CRHF | CVG Global Supply Management | Component Engineering | AFS (Rheault) | Component Eng | High | BCP | Analytical QC Instrament Replacements | 2021 | 14.23 | 14.23 | 14.23 | 14.23 | 14.23 | 14.23 | 14.23 | 14.23 | 14.23 | 0 | 0 | 0
TBD | NA | CRHF | CVG Global Supply Management | Component Engineering | AFS (Rheault) | Component Eng | High | BCP | Analytical QC Instrament Replacements | 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-Very High 2-High 3-Medium 4-Low 5-Very Low

## DirectExpenses
Project Name | MA60365 - 2nd Source for Elasthane/Polyurethane
WBSNumber | ExpenseCategory | Description | FinYear | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR
MA60365.MEC | Expensed Material, tooling, and spares | 1847336 - Glass Filled Retainer | 2020 | MAY: 1.2; JUN: 0
MA60365.MEC | Expensed Material, tooling, and spares | M950940A002 Header - OQ/PQ parts | 2023 | JUN: 0; OCT: 11227.5
MA60365.MEC | Expensed Material, tooling, and spares | M950940A002 Header - Feasibility | 2023 | JUN: 0
MA60365.MEC | Expensed Material, tooling, and spares | 411603 Connector Assembly - OQ/PQ parts | 2022 | JUN: 0; JUL: 4728.75
MA60365.MEC | Expensed Material, tooling, and spares | 411603 Connector Assembly - Char parts | 2020 | MAY: 12.61; JUN: 0
MA60365.MEC | Expensed Material, tooling, and spares | 411603 Connector Assembly - Feasibility | 2020 | MAY: 12.61
MA60365.MEC | Expensed Material, tooling, and spares | 411603 Connector Assembly - Feasibility | 2022 | MAY: 630.5
MA60365.MEC | Expensed Material, tooling, and spares | M965612A001 SSM VAA - OQ/PQ parts$96 | 2020 | MAY: 145.63; DEC: 29200
MA60365.MEC | Expensed Material, tooling, and spares | M965612A001 SSM VAA - Char parts$96 | 2020 | MAY: 145.63; NOV: 29200
MA60365.MEC | Expensed Material, tooling, and spares | M965612A001 SSM VAA - Feasibility parts - $96 | 2020 | MAY: 145.63; FEB: 5000; MAR: 5000
MA60365.MEC | Expensed Material, tooling, and spares | M965612A001 SSM VAA - Feasibility parts - $96 | 2021 | AUG: 19000
MA60365.MEC | Expensed Material, tooling, and spares | M964250A002 SSM - OQ/PQ parts - $144 | 2020 | MAY: 3.64
MA60365.MEC | Expensed Material, tooling, and spares | M964250A002 SSM - OQ/PQ parts - $144 | 2021 | SEP: 40000
MA60365.MEC | Expensed Material, tooling, and spares | M964250A002 SSM - Char parts | 2020 | MAY: 3.64; OCT: 1200
MA60365.MEC | Expensed Material, tooling, and spares | M964250A002 SSM - Char parts | 2021 | JUN: 30000
MA60365.MEC | Expensed Material, tooling, and spares | M939341A003 First Shot Mold (FSM) - Feasibility - $3.64 | 2020 | MAY: 3.64
MA60365.MEC | Expensed Material, tooling, and spares | M960762A001 VAA - OQ/PQ parts | 2020 | MAY: 130
MA60365.MEC | Expensed Material, tooling, and spares | M960762A001 VAA - Char parts | 2020 | MAY: 130; SEP: 11700
MA60365.MEC | Expensed Material, tooling, and spares | M960762A001 VAA - Feasibility parts | 2020 | MAY: 130
MA60365.MEC | Expensed Material, tooling, and spares | M961814A001 Molding - OQ/PQ parts | 2020 | MAY: 19.41; AUG: 7278.75
MA60365.MEC | Expensed Material, tooling, and spares | M961814A001 Molding - OQ/PQ parts | 2021 | AUG: 9000; FEB: 10000
MA60365.MEC | Expensed Material, tooling, and spares | M961814A001 Molding - Char parts | 2020 | MAY: 19.41; JUN: 4000
MA60365.MEC | Expensed Material, tooling, and spares | M961814A001 Molding - Char parts | 2021 | JUN: 9000; JUL: 6000; DEC: 6000
MA60365.MEC | Expensed Material, tooling, and spares | M961814A001 Molding - Feasibility - $19.41 | 2020 | MAY: 19.41
MA60365.MEC | Expensed Material, tooling, and spares | M961814A001 Molding - Feasibility - $19.41 | 2021 | SEP: 6000