## AssignLive Pivote
Teams - FisYear | Design and Systems Engineering - 2022

## AssignData
WBSNumber | ProjectName | Team | RequiredSkills | ResourceName | Month | value
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Sanders, Matt | MAY | 0.5
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Sanders, Matt | JUN | 0.67
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Sanders, Matt | JUL | 0.11
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Sanders, Matt | AUG | 0.45
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Sanders, Matt | SEP | 0.45
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Sanders, Matt | OCT | 0.11
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Sanders, Matt | NOV | 0
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Sanders, Matt | DEC | 0.59
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Sanders, Matt | JAN | 0
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Sanders, Matt | FEB | 0
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Sanders, Matt | MAR | 0
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Sanders, Matt | APR | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Lohstreter, Lance | MAY | 0.56
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Lohstreter, Lance | JUN | 0.99
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Lohstreter, Lance | JUL | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Lohstreter, Lance | AUG | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Lohstreter, Lance | SEP | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Lohstreter, Lance | OCT | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Lohstreter, Lance | NOV | 0.23
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Lohstreter, Lance | DEC | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Lohstreter, Lance | JAN | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Lohstreter, Lance | FEB | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Lohstreter, Lance | MAR | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Lohstreter, Lance | APR | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Yon, Zach | MAY | 0.99
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Yon, Zach | JUN | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Yon, Zach | JUL | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Yon, Zach | AUG | 0.98
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Yon, Zach | SEP | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Yon, Zach | OCT | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Yon, Zach | NOV | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Yon, Zach | DEC | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Yon, Zach | JAN | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Yon, Zach | FEB | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Yon, Zach | MAR | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Yon, Zach | APR | 0
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Larson, Jason | MAY | 0.45
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Larson, Jason | JUN | 0.88
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Larson, Jason | JUL | 0.34
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Larson, Jason | AUG | 0.55
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Larson, Jason | SEP | 0.56
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Larson, Jason | OCT | 0.45
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Larson, Jason | NOV | 0
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Larson, Jason | DEC | 0
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Larson, Jason | JAN | 0
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Larson, Jason | FEB | 0
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Larson, Jason | MAR | 0
MA61634.MEC | API Insourcing | Design and Systems Engineering | Des Eng | Larson, Jason | APR | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Sanders, Matt | MAY | 0.89
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Sanders, Matt | JUN | 0.11
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Sanders, Matt | JUL | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Sanders, Matt | AUG | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Sanders, Matt | SEP | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Sanders, Matt | OCT | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Sanders, Matt | NOV | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Sanders, Matt | DEC | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Sanders, Matt | JAN | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Sanders, Matt | FEB | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Sanders, Matt | MAR | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Sanders, Matt | APR | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Larson, Jason | MAY | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Larson, Jason | JUN | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Larson, Jason | JUL | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Larson, Jason | AUG | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Larson, Jason | SEP | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Larson, Jason | OCT | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Larson, Jason | NOV | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Larson, Jason | DEC | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Larson, Jason | JAN | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Larson, Jason | FEB | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Larson, Jason | MAR | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Larson, Jason | APR | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Lohstreter, Lance | MAY | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Lohstreter, Lance | JUN | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Lohstreter, Lance | JUL | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Lohstreter, Lance | AUG | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Lohstreter, Lance | SEP | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Lohstreter, Lance | OCT | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Lohstreter, Lance | NOV | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Lohstreter, Lance | DEC | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Lohstreter, Lance | JAN | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Lohstreter, Lance | FEB | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Lohstreter, Lance | MAR | 0
CR00342.MEC | Diabetes 8xx Pump | Design and Systems Engineering | Sys | Lohstreter, Lance | APR | 0
CR62134.MEC | EV ICD Cap | Design and Systems Engineering | Des Eng | Sanders, Matt | MAY | 0
CR62134.MEC | EV ICD Cap | Design and Systems Engineering | Des Eng | Sanders, Matt | JUN | 0
CR62134.MEC | EV ICD Cap | Design and Systems Engineering | Des Eng | Sanders, Matt | JUL | 0.78
CR62134.MEC | EV ICD Cap | Design and Systems Engineering | Des Eng | Sanders, Matt | AUG | 0
CR62134.MEC | EV ICD Cap | Design and Systems Engineering | Des Eng | Sanders, Matt | SEP | 0
CR62134.MEC | EV ICD Cap | Design and Systems Engineering | Des Eng | Sanders, Matt | OCT | 0
CR62134.MEC | EV ICD Cap | Design and Systems Engineering | Des Eng | Sanders, Matt | NOV | 0
CR62134.MEC | EV ICD Cap | Design and Systems Engineering | Des Eng | Sanders, Matt | DEC | 0
CR62134.MEC | EV ICD Cap | Design and Systems Engineering | Des Eng | Sanders, Matt | JAN | 0
CR62134.MEC | EV ICD Cap | Design and Systems Engineering | Des Eng | Sanders, Matt | FEB | 0
CR62134.MEC | EV ICD Cap | Design and Systems Engineering | Des Eng | Sanders, Matt | MAR | 0
CR62134.MEC | EV ICD Cap | Design and Systems Engineering | Des Eng | Sanders, Matt | APR | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Sanders, Matt | MAY | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Sanders, Matt | JUN | 0.78
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Sanders, Matt | JUL | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Sanders, Matt | AUG | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Sanders, Matt | SEP | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Sanders, Matt | OCT | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Sanders, Matt | NOV | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Sanders, Matt | DEC | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Sanders, Matt | JAN | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Sanders, Matt | FEB | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Sanders, Matt | MAR | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Sanders, Matt | APR | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Larson, Jason | MAY | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Larson, Jason | JUN | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Larson, Jason | JUL | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Larson, Jason | AUG | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Larson, Jason | SEP | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Larson, Jason | OCT | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Larson, Jason | NOV | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Larson, Jason | DEC | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Larson, Jason | JAN | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Larson, Jason | FEB | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Larson, Jason | MAR | 0
NE07341.MEC | Glass Feedthrough for Sensing | Design and Systems Engineering | Des Eng | Larson, Jason | APR | 0
CR62176.MEC | LINQ HF | Design and Systems Engineering | Des Eng | Sanders, Matt | MAY | 0.89
CR62176.MEC | LINQ HF | Design and Systems Engineering | Des Eng | Sanders, Matt | JUN | 0
CR62176.MEC | LINQ HF | Design and Systems Engineering | Des Eng | Sanders, Matt | JUL | 0
CR62176.MEC | LINQ HF | Design and Systems Engineering | Des Eng | Sanders, Matt | AUG | 0
CR62176.MEC | LINQ HF | Design and Systems Engineering | Des Eng | Sanders, Matt | SEP | 0
CR62176.MEC | LINQ HF | Design and Systems Engineering | Des Eng | Sanders, Matt | OCT | 0
CR62176.MEC | LINQ HF | Design and Systems Engineering | Des Eng | Sanders, Matt | NOV | 0
CR62176.MEC | LINQ HF | Design and Systems Engineering | Des Eng | Sanders, Matt | DEC | 0
CR62176.MEC | LINQ HF | Design and Systems Engineering | Des Eng | Sanders, Matt | JAN | 0
CR62176.MEC | LINQ HF | Design and Systems Engineering | Des Eng | Sanders, Matt | FEB | 0
CR62176.MEC | LINQ HF | Design and Systems Engineering | Des Eng | Sanders, Matt | MAR | 0
CR62176.MEC | LINQ HF | Design and Systems Engineering | Des Eng | Sanders, Matt | APR | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Sanders, Matt | MAY | 0.22
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Sanders, Matt | JUN | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Sanders, Matt | JUL | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Sanders, Matt | AUG | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Sanders, Matt | SEP | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Sanders, Matt | OCT | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Sanders, Matt | NOV | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Sanders, Matt | DEC | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Sanders, Matt | JAN | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Sanders, Matt | FEB | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Sanders, Matt | MAR | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Sanders, Matt | APR | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Lohstreter, Lance | MAY | 0.87
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Lohstreter, Lance | JUN | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Lohstreter, Lance | JUL | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Lohstreter, Lance | AUG | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Lohstreter, Lance | SEP | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Lohstreter, Lance | OCT | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Lohstreter, Lance | NOV | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Lohstreter, Lance | DEC | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Lohstreter, Lance | JAN | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Lohstreter, Lance | FEB | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Lohstreter, Lance | MAR | 0
MA50100.MEC | MECC Development Product Support | Design and Systems Engineering | Des Eng | Lohstreter, Lance | APR | 0
CR61597.MEC | Micra EL Battery | Design and Systems Engineering | Des Eng | Sanders, Matt | MAY | 0.99
CR61597.MEC | Micra EL Battery | Design and Systems Engineering | Des Eng | Sanders, Matt | JUN | 0
CR61597.MEC | Micra EL Battery | Design and Systems Engineering | Des Eng | Sanders, Matt | JUL | 0
CR61597.MEC | Micra EL Battery | Design and Systems Engineering | Des Eng | Sanders, Matt | AUG | 0
CR61597.MEC | Micra EL Battery | Design and Systems Engineering | Des Eng | Sanders, Matt | SEP | 0
CR61597.MEC | Micra EL Battery | Design and Systems Engineering | Des Eng | Sanders, Matt | OCT | 0
CR61597.MEC | Micra EL Battery | Design and Systems Engineering | Des Eng | Sanders, Matt | NOV | 0
CR61597.MEC | Micra EL Battery | Design and Systems Engineering | Des Eng | Sanders, Matt | DEC | 0
CR61597.MEC | Micra EL Battery | Design and Systems Engineering | Des Eng | Sanders, Matt | JAN | 0
CR61597.MEC | Micra EL Battery | Design and Systems Engineering | Des Eng | Sanders, Matt | FEB | 0
CR61597.MEC | Micra EL Battery | Design and Systems Engineering | Des Eng | Sanders, Matt | MAR | 0
CR61597.MEC | Micra EL Battery | Design and Systems Engineering | Des Eng | Sanders, Matt | APR | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Nguyen, Andrew | MAY | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Nguyen, Andrew | JUN | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Nguyen, Andrew | JUL | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Nguyen, Andrew | AUG | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Nguyen, Andrew | SEP | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Nguyen, Andrew | OCT | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Nguyen, Andrew | NOV | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Nguyen, Andrew | DEC | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Nguyen, Andrew | JAN | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Nguyen, Andrew | FEB | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Nguyen, Andrew | MAR | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Nguyen, Andrew | APR | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | MAY | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | JUN | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | JUL | 0.9
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | AUG | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | SEP | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | OCT | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | NOV | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | DEC | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | JAN | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | FEB | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | MAR | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | APR | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Ernster, Timothy | MAY | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Ernster, Timothy | JUN | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Ernster, Timothy | JUL | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Ernster, Timothy | AUG | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Ernster, Timothy | SEP | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Ernster, Timothy | OCT | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Ernster, Timothy | NOV | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Ernster, Timothy | DEC | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Ernster, Timothy | JAN | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Ernster, Timothy | FEB | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Ernster, Timothy | MAR | 0
MA50306.MEC | MECC Reactive CAPA | Design and Systems Engineering | Des Eng | Ernster, Timothy | APR | 0
MA62081.MEC | Micra CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | MAY | 0
MA62081.MEC | Micra CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | JUN | 0
MA62081.MEC | Micra CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | JUL | 0
MA62081.MEC | Micra CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | AUG | 0
MA62081.MEC | Micra CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | SEP | 0
MA62081.MEC | Micra CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | OCT | 0
MA62081.MEC | Micra CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | NOV | 0
MA62081.MEC | Micra CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | DEC | 0
MA62081.MEC | Micra CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | JAN | 0
MA62081.MEC | Micra CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | FEB | 0
MA62081.MEC | Micra CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | MAR | 0
MA62081.MEC | Micra CAPA | Design and Systems Engineering | Des Eng | Sanders, Matt | APR | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Sanders, Matt | MAY | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Sanders, Matt | JUN | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Sanders, Matt | JUL | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Sanders, Matt | AUG | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Sanders, Matt | SEP | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Sanders, Matt | OCT | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Sanders, Matt | NOV | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Sanders, Matt | DEC | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Sanders, Matt | JAN | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Sanders, Matt | FEB | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Sanders, Matt | MAR | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Des Eng | Sanders, Matt | APR | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Sanders, Matt | MAY | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Sanders, Matt | JUN | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Sanders, Matt | JUL | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Sanders, Matt | AUG | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Sanders, Matt | SEP | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Sanders, Matt | OCT | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Sanders, Matt | NOV | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Sanders, Matt | DEC | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Sanders, Matt | JAN | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Sanders, Matt | FEB | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Sanders, Matt | MAR | 0
MA60364.MEC | Common Pin Material for Glass Feedthroug | Design and Systems Engineering | Sys | Sanders, Matt | APR | 0